## Sheet1
File |  |  | Description | Status | Schedule
db/ |  | seeds.rb | news up some entries in the database | MVP instances added | Saturday 15 Dec
|  | spending_tracker.sql | contains the db schema | MVP schema completed | Thursday 13 Dec
|  | sql_runner.rb | tool for easy sql-ruby connection | completed | Thursday 13 Dec
models/ |  | merchants.rb | contains merchant class, methods and functions | MVP actions completed | Saturday 15 Dec
|  | purchases.rb | contains purchase class, methods and functions | MVP actions completed | Saturday 15 Dec
|  | tags.rb | contains tag class, methods and functions | MVP actions completed | Saturday 15 Dec
|  | users.rb | contains user class, methods and functions | MVP actions completed | Saturday 15 Dec
specs/ |  | merchants_specs.rb | TDD for merchant class | MVP tests not completed | Saturday 15 Dec
|  | purchases_specs.rb | TDD for purchase class | MVP tests not completed | Saturday 15 Dec
|  | tags_specs.rb | TDD for spec class | MVP tests not completed | Saturday 15 Dec
|  | users_specs.rb | TDD for user class | MVP tests not completed | Saturday 15 Dec
|  | app.rb | main app controller | MVP completed | Sunday 16 Dec
controllers/ |  | merchants_controller.rb | merchants views controller | MVP completed | Sunday 16 Dec
|  | purchases_controller.rb | purchases views controller | MVP completed | Sunday 16 Dec
|  | tags_controller.rb | tags views controller | MVP completed | Sunday 16 Dec
|  | user_controller.rb | users view controller | MVP completed | Sunday 16 Dec
views/ |  | layout.erb | wrapper for whole of the app | MVP completed | Sunday 16 Dec
|  | index.erb | home page yield | MVP completed | Sunday 16 Dec
| merchants/ | index.erb | merchants pages yield | MVP completed | Sunday 16 Dec
| purchases/ | index.erb | purchases pages yield | MVP completed | Sunday 16 Dec
| tags/ | index.erb | tags pages yield | MVP completed | Sunday 16 Dec
| users/ | index.erb | users pages yield | MVP completed | Sunday 16 Dec
public/ |  | styles.css | makes the app look pretty | started | Wednesday 19 Dec
|  | TODO | add in test asserts for SQL/ruby ==
draw up proto persona for dril
make slideshow of user journey

## Sheet2
File | Description | Status
INFO |  |  | ACTIONS
make the dashboard the home page
change the wording for Tags, Merchants etc
add labels to forms